**City of Buffalo Lead Hazard Control Program**

**Legislate, Collaborate, Educate and Remediate**

1. $250,000 will be provided annually for lead issues through raising the Rental Registration Fee, additionally $205,000 in Community Development Block Grants will be provided.

*(Rental Registration bills mailed in January 2017, fees in hand by April 1, 2017, CDBG funds are available by July 1, 2016)*

1. Funds will be provided in partnership with CDBG, HOME, Rental Registration, GHHI, CFGB, Erie County and the New York State Attorney General’s office to remediate at least 150 units, annually.

*(Mid-September 2016)*

1. Strengthen City Charter, City Code and Rental Registry to require landlord lead certification.

*(Mid-July 2016)*

1. Certificates of occupancy will not be granted to dwellings with lead-based paint hazards.

*(Mid-July 2016)*

1. Property managers will be required to be lead-safe certified.

*(Mid-July 2016)*

1. UNYSE will do lead testing upon referral from city building inspectors.

*(Immediately available)*

1. BNET will conduct concentrated code enforcement in zip codes with the highest percentage of lead paint hazards (14211, 14213, 14215).

*(June 1, 2016)*

1. 311 will have a dedicated “lead line” take calls about lead paint concerns from city residents.

*(July 1, 2016)*

1. Lead education will be provided on city website, in user fee bills, during clean sweeps, translated in various languages, and on public access television and city building permit applications.

*(Rolling out across various platforms starting July 1, 2016)*

1. Collaboration will be increased with Erie County, the Green & Healthy Homes Initiative and the Community Foundation for Greater Buffalo and Buffalo Public Schools.

*(Immediately)*

1. Buffalo MBE, WBE, Section 3 and small businesses will be trained to become lead certified.

*(Fall 2016 or earlier based course offering availability)*